## Sheet1
Metric | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Points Committed | 5 | 3 | 3 | 2
Points Delivered | 0 | 2 | 3 | 5
Stories Committed | 2 | 2 | 1 | 2
Stories Accepted | 0 | 1 | 1 | 3
Features Committed | 1. Government create a new opportunity | 1. Government create a new opportunity | 1. Government manage all opportunities | 1. Government publish opportunity. 2. Contractor view published opportunities
Features Accepted | None | 1. Government create a new opportunity | 1. Government manage all opportunities | 1. Government publish opportunity. 2. Contractor view published opportunities 3. Government edit opportunity